## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to develpoment of python based stock & ETF signal generation platform | MUST HAVE | No dependency | Polipalli Sai | 3- Completed
S1 | S1 | US-002 | Project goals, scope, data flow | SHOULD HAVE | online research | Polipalli Sai | 3- Completed
S2 | S2 | US-003 | Planning Architecture for dashboard | MUST HAVE | Figma | Polipalli Sai | 3- Completed
S2 | S2 | US-004 | Environment Setup (Python , Libraries, etc) | MUST HAVE | VS Code, Python | Polipalli Sai | 3- Completed
S3 | S3 | US-005 | Streamlit dashboard with some charts and indicators | MUST HAVE | streamlit | Polipalli Sai | 3- Completed
S4 | S4 | US-006 | Dashboard integration with sample data | MUST HAVE | plotly | Polipalli Sai | 3- Completed
S4 | S4 | US-007 | Coordinate with other teams for output requirements | SHOULD HAVE | team discussions | Polipalli Sai | 3- Completed
S5 | S5 | US-008 | integration ML outputs into dashboard | MUST HAVE | ML output | Polipalli Sai | 3- Completed
S6 | S6 | US-009 | Backtesting Visualization | MUST HAVE | Backtesting | Polipalli Sai | 3- Completed
S7 | S7 | US-010 | Documentation and PPT Preparation | MUST HAVE | DOCS,PPT | Polipalli Sai | 3- Completed
S8 | S8 | US-011 | Final Testing & Deployment | MUST HAVE | Cloud Platform/Github | Polipalli Sai | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 25 | 14 | 11 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to develpoment of python based stock & ETF signal generation platform | 2025-11-26 | 2025-12-02 | Polipalli Sai | Others | 3 – Completed | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Project goals, scope, data flow | 2025-12-03 | 2025-12-09 | Polipalli Sai | Research | 3 – Completed | 4 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Agile Documentation Setup (Sprint, Stories, GitHub Flow) | 2025-12-10 | 2025-12-16 | Polipalli Sai | Research | 3 – Completed | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Planning Architecture for dashboard | 2025-12-17 | 2025-12-23 | Polipalli Sai | Figma | 3 – Completed | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-002 | 5 | Environment Setup (Python , Libraries, etc) | 2025-12-17 | 2025-12-23 | Polipalli Sai | VS Code | 3 – Completed | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 6 | Streamlit dashboard with some charts and indicators | 2025-12-24 | 2025-12-30 | Polipalli Sai | Coding | 3 – Completed | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-003 | 7 | Dashboard integration with sample data | 2025-12-24 | 2025-12-30 | Polipalli Sai | Coding | 3 – Completed | 3 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG
US-004 | 8 | Coordinate with other teams for output requirements | 2025-12-31 | 2026-01-06 | Polipalli Sai | Analysis | 3 – Completed | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 9 | integration outputs into dashboard | 2026-01-07 | 2026-01-13 | Polipalli Sai | Integration | 3 – Completed | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG
US-005 | 10 | Final Testing & Deployment | 2026-01-14 | 2026-01-21 | Polipalli Sai | System Test | 3 – Completed | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint1 | Day2 | Initial lack of clarity on overall AI Stock Signal project scope and expected outputs | Discussed project objectives with mentor and reviewed reference materials
Sprint1 | Day4 | Confusion about role-specific responsibilities between Dashboard, ML, and Backtesting teams | Conducted cross-team discussion to clearly define inputs and outputs
Sprint2 | Day6 | Difficulty understanding Agile story writing and MOSCOW prioritization | Reviewed Agile template and clarified doubts during mentor-led session
Sprint2 | Day8 | Uncertainty in designing dashboard workflow before final ML outputs | Created a flexible dashboard wireframe that supports dynamic ML data
Sprint3 | Day11 | Issues in setting up Streamlit environment and library compatibility | Reinstalled dependencies and validated setup using sample applications
Sprint3 | Day13 | Challenges in rendering interactive charts with stock data | Referred official documentation and tested multiple visualization libraries
Sprint4 | Day16 | Delay in receiving finalized data format from Backtesting team | Used mock JSON data to continue dashboard development
Sprint5 | Day22 | Difficulty integrating ML Buy/Hold/Sell signals with confidence scores | Coordinated with ML team to standardize signal output structure
Sprint6 | Day27 | Performance issues when loading multiple dashboard components | Optimized data loading and applied caching techniques in Streamlit
Sprint7 | Day31 | Uncertainty around alert trigger conditions and notification flow | Designed configurable alert logic and validated with mentor feedback
Sprint7 | Day31 | Uncertainty around alert trigger conditions and notification flow | Designed configurable alert logic and validated with mentor feedback

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint1 | 11/26/2025 | 2025-02-12 | Samruddhi Junavane,Polipalli Sai,Tarun,Shamrutha | Reviewing project documentation and understanding stock market basics | Assuming requirements without clarification | Participating in mentor and team discussions | Conducted requirement clarification session and aligned on project scope
2 | Sprint2 | 2025-03-12 | 2025-09-12 | Tarun | Structuring Agile stories and sprint timelines | Writing vague or task-level stories | Following Agile methodology consistently | Refined user stories using MOSCOW prioritization
3 | Sprint3 | 2025-10-12 | 12/16/2025 | Tarun,Polipalli Sai,Samruddhi Junavane,Shamrutha | Setting up Streamlit dashboard and Python environment | Delaying UI testing | Practicing incremental coding and testing | Successfully completed environment setup and basic dashboard layout
4 | Sprint4 | 12/17/2025 | 12/23/2025 | Tarun,Samruddhi Junavane,Shamrutha, Polipalli Sai | Integrating sample stock data and visualizations | Waiting for finalized ML outputs | Coordinating with ML and backtesting teams | Used mock data to complete dashboard visual components
5 | Sprint5 | 12/24/2025 | 12/30/2025 | Tarun | Integrating ML Buy/Sell signals into dashboard | Hardcoding values in UI | Using dynamic and configurable data pipelines | Standardized ML signal format and integrated it into the dashboard
6 | Sprint6 | 12/31/2025 | 2026-06-01 | Tarun,Shamrutha | Integrating alert functionality and trading notifications into the dashboard | Pushing changes without cross-team confirmation | Incremental testing after every integration | Resolved integration inconsistencies and stabilized dashboard features
7 | Sprint7 | 2026-07-01 | 1/13/2026 | Tarun,Samruddhi Junavane,Shamrutha,Polipalli Sai | Validating end-to-end data flow across all dashboard features | Ignoring minor UI inconsistencies | Peer reviews and team feedback sessions | Finalized feature set and prepared the system for demo and documentation
8 | Sprint8 | 1/14/2026 | 1/28/2026 | Samruddhi Junavane,Pollipalli Sai | Demo Video,Documentation,PPT | Leaving presentation and docs to last minute | Team collaboration | Completed PPT, demo video, final documentation, and project submission